## Task List
Task ID | Owner | Milestone | Commit Message | Title / Scope | Weight | Start Date and Time | Completed Date and Time | Files | Details
1 | Mert Koçyiğit | M1 | feat: add base cell model and shared contracts | Base cell model and shared contracts | 70 | 01/05/2026 09:59 | 04/05/2026 18:00 | src/cell/Cell.java src/cell/EmptyCell.java src/cell/Road.java src/interfaces/Connectable.java src/interfaces/Producible.java src/enums/UtilityType.java src/enums/ServiceType.java src/enums/ResourceType.java | Created the core Cell hierarchy foundation, empty/road cells, shared interfaces, and common enums.
2 | Elif Çarıkçı | M2 | feat: implement map loading and cell creation | Map loading and cell creation | 60 | 04/05/2026 11:00 | 08/05/2026 17:29 | src/city/City.java | Implemented city map loading, parsing, validation, and cell creation from map symbols.
3 | Deren Kocabaş | M2 | feat: add zone types and production logic | Zone types and production logic | 80 | 08/05/2026 12:00 | 13/05/2026 18:59 | src/cell/zone/Zone.java src/cell/zone/Housing.java src/cell/zone/Industrial.java src/cell/zone/Commercial.java | Implemented zone abstraction and housing, industrial, and commercial production behavior.
4 | Arda Abacı | M3 | feat: add utility providers | Utility providers | 50 | 12/05/2026 14:00 | 25/05/2026 14:44 | src/cell/utility/UtilityProvider.java src/cell/utility/PowerPlant.java src/cell/utility/WaterStation.java src/cell/utility/InternetHub.java | Implemented utility provider abstraction and electricity, water, and internet provider classes.
5 | Arda Abacı | M3 | feat: add service providers | Service providers | 50 | 25/05/2026 14:45 | 25/05/2026 18:16 | src/cell/service/ServiceProvider.java src/cell/service/PoliceStation.java src/cell/service/Hospital.java src/cell/service/School.java | Implemented service provider abstraction and security, health, and education provider classes.
6 | Deren Kocabaş | M3 | feat: implement city simulation loop | City simulation loop | 80 | 17/05/2026 15:00 | 21/05/2026 21:00 | src/city/Simulation.java | Implemented the main city simulation loop and tick-based update flow.
7 | Mert Koçyiğit | M4 | feat: add command line runner | Command line runner | 40 | 21/05/2026 10:30 | 23/05/2026 20:00 | src/ObjectVilleGame.java | Added command line entry point for running the ObjectVille game/simulation.
8 | Elif Çarıkçı | M4 | docs: add project report | Project report | 70 | 23/05/2026 09:59 | 27/05/2026 18:00 | report/ObjectVilleII_Project_Report.pdf | Prepared and added the final project report document.
9 | Arda Abacı | M4 | build: add build scripts and runnable jar | Build scripts and runnable JAR | 60 | 26/05/2026 12:00 | 31/05/2026 14:18 | build.bat build.sh manifest.mf ObjectVilleGame.jar | Added build scripts, manifest file, and runnable JAR package.
10 | Mert Koçyiğit | M5 | chore: add task point spreadsheet | Task point spreadsheet | 50 | 29/05/2026 12:59 | 31/05/2026 18:59 | Task_Point_System.xlsx | Added the corrected task point spreadsheet according to the submission plan.
11 | Elif Çarıkçı | M5 | chore: add developer contribution list | Developer contribution list | 30 | 31/05/2026 12:00 | 02/06/2026 21:00 | Developer_List.csv | Added developer contribution list as a separate CSV file for the final submission.

## Developer List
Developer | Tasks | Task IDs | Milestones | Total Weight | Contribution % | Score | Primary Role
Mert Koçyiğit | 3 | 1, 7, 10 | M1, M4, M5 | 160 | 25% | 100 | Core cell model, interfaces, enums; CLI runner; task spreadsheet
Elif Çarıkçı | 3 | 2, 8, 11 | M2, M4, M5 | 160 | 25% | 100 | Map loading & cell creation (City); project report; developer list
Deren Kocabaş | 2 | 3, 6 | M2, M3 | 160 | 25% | 100 | Zone hierarchy & production logic; city simulation loop
Arda Abacı | 3 | 4, 5, 9 | M3, M4 | 160 | 25% | 100 | Utility providers; service providers; build scripts & runnable JAR
TEAM TOTAL | 11 |  |  | 640 |  | 100 | Average score across all developers
TEAM AVERAGE |  |  |  | 160 |  |  | Expected points per developer